## Sheet1
TODO |  | Deadline | Who | What | Notes
Venues | Kickoff | 4-6 months out |  | Book [venue] for [Dates & time]
| Hackday | 4-6 months out |  | Book [venue] for [Dates & time]
| Extra course/hackday | 4-6 months out |  | Book [venue] for [Dates & time]
| Pitch night | 4-6 months out |  | Book [venue] for [Dates & time]
| After party | 4-6 months out |  | Book [venue] for [Dates & time]
Data |  | 4-6 months out |  | Find a good dataset
|  | 3-4 months out |  | Brainstorm list of challenges for pitch & kaggle competition
|  | 3-4 months out | [Data provider] | Prepare a subsample of the data to inspect
|  | 2-3 months out |  | Inspect the subsample and provide feedback for sampling, cleaning, etc.
|  | 2-3 months out | [Data provider] | Finalise dataset
|  | 2-3 months out |  | Decide on challenges, data distribution method, NDA
|  | 1-2 months out | [Data provider] | Prepare data for distribution, finalize NDA
|  | 1-2 months out |  | If possible, figure out a way to have people sign the NDA online
|  | 1 month out |  | Double check data before release
|  | 1 month out |  | Prepare data walkthrough for hackday
Comms | Website | 4-6 months out |  | Create a logo and other comms material | E.g. wordpress (connect to mailchimp)
|  | 4-6 months out |  | Set up website for information and registration
|  | 4-6 months out |  | Open up registrations
| Social Media | 3-4 months out |  | Update Facebook + Twitter and start posting announcements for event dates
|  | 0-3 months out |  | Continue to post announcements, dates & tips
|  | 2-3 months out |  | Post announcements in other Meetups
| Email | 4-6 months out |  | Set up email address
|  | 4-6 months out |  | Create mailout templates | E.g. mailchimp
Budget | Sponsoring | 4-6 months out |  | Find sponsors
|  | 4-6 months out |  | Check in with all sponsors to make sure they are OK with chosen dataset
Event prep | General | 4-6 months out |  | Get first-aid certifications if required
|  | 3-4 months out |  | Find a photographer and videographer
|  | 3-4 months out |  | Check with Kaggle if it's possible to use Kaggle In-Class (was allowed in the past if it's a community event)
|  | 3-4 months out |  | Check & arrange venue WIFI, security & other requirements
|  | 1-2 months out |  | Create submission template with guidelines on how to make a good submission | E.g. "what's the objective", "what was your process", "what are your actionable recommendations"
|  | 1-2 months out |  | Set up Kaggle competition
|  | 1-2 months out |  | Prepare post-event survey
|  | 3-4 months out |  | Design big award cheques and have them printed
| Launch | 1 month out |  | Create launch event presentation slides with datathon concept + goals + schedule | See example
|  | 1 month out |  | Print out datathon logo + arrow to left/right (x3 each)
|  | 1 month out |  | Print out sign "Non-Disclosure Agreements (NDAs)" x4
|  | 1 month out |  | Print out sign "Place signed NDAs here. Make sure you filled out XXX and XXX. Invalid NDA = no data."
|  | 1 month out |  | Print out sign "Room full? Slides will be emailed & NDAs can also be found outside the room"
|  | 1 month out |  | Print out XXX NDAs at a print shop, unless it's an online process
|  | 1 month out |  | Buy/find NDA signing supplies (pens, tape, big boxes)
| Hackday | 1-2 months out |  | Create hackday program, include venue map, add logo to (arrow) signs (and laminate)
|  | 3-4 months out |  | Contact 3-4 experts who would be willing to give a tutorial presentation on the hackday (on data wrangling, mapping, presenting, etc.)
|  | 3-4 months out |  | Contact 3-4 experts who would be willing to be tutors on the hackday (helping with technical questions)
|  | 1 month out |  | Buy team building activity supplies, if needed (e.g. name stickers)
|  | 1 month out |  | Buy data station supplies (rope, tape, scissors)
|  | 1 month out |  | Buy lanyards for mentors/organisers
|  | 1 month out |  | Create slides to show how team formation works
|  | 1 month out |  | Create todo list for hackday morning setup and night breakdown, divide tasks
|  | 1 month out |  | Print programs
|  | 1 month out |  | Print sign "Sign in desk"
|  | 1 month out |  | Print sign "Data station" x3
|  | 1 month out |  | Print sign "Refreshments station" x 3
|  | 1 month out |  | Print sign with arrows pointing right (refreshments, data, presentation, co-working) and left (co-working)
|  | 1 month out |  | Print sign "Presentation area" x2
|  | 1 month out |  | Print sign "Co-working space" x 4
|  | 1 month out |  | Print logo x 6 for doors
|  | 1 month out |  | Print signs for signup desk (welcome, grab namesticker, colored dots, etc.)
| Pitch night | 3-4 months out |  | Contact 3-4 industry leaders/experts who would be willing to judge the presentations
|  | 1 month out |  | Create pitch night introduction presentation | See example
|  | 1 month out |  | Buy big cheque sharpie to write team names (big one)
|  | 1 month out |  | Buy little bell to notify pitches that they have 1 minute left
|  | 1 month out |  | Define clear judging criteria | See example
|  | 1 month out |  | Set up audience vote before pitch night | If desired